## Sheet1
Stage One (November – December)		Stage Two (December – February)		Stage Three (February – March)	Stage Four (March)		Stage Five (March – April)	Stage Six (April – May)	REPORT
								Create and thoroughly test the application
Create mocks for the look and feel of the interface	Create a basic working neural network for XOR

Rough style guidelines for the UI
	Prototype to base true neural network on	Gather a dataset to train the network on	Create the base network to recognise numberplate digits

		Dataset of numberplate numbers and letters
			Basic non-trained network	Train the network on the earlier gathered dataset

				Test the network using real example photos	Create the front end for the user to interact with

						Create database backend to link to the front end	Link the network with the frontend to enable the feeding of car numberplate images
				Dataset of numberplate numbers and letters
					Functioning interface for users to interact with that links to the network

								Finished application